## Purchase FMS Sheet
| 0.41667 | 9 | 19
What | Indent Received | [8 empty] | STEP 1 - Indent Verification - Specification |  |  |  |  | STEP 2 - Check Store Availablity | [5 empty] | STEP 3 - Float RFQ |  |  |  |  | STEP 4 - PO Creation
Who | Purchase Team | [8 empty] | Jane Doe ¦ John Doe |  |  |  |  | Alice ¦ Bob | [5 empty] | Bruce Wayne |  |  |  |  | Alice Johnson ¦ Bob Smith
How | Filling Indent for Material Form | [8 empty] | Check the Received Indent |  |  |  |  | Check Store Availablity | [5 empty] | Via Mail |  |  |  |  | Discussion with Management
When | Materials Required | [8 empty] | 0.16667 |  |  |  |  | 0.16667 | [5 empty] | 1 | 0.125 | 1 day for tailor made items and 3hrs for readymade |  |  | 0.16667
Timestamp | Itemwise Indent No. | Filled By | Project ID | Project Name | Item Description | Quantity | Required Date | Attachment | Item Type | Planned | Actual | Status | Time Delay | Remarks | Planned | Actual | Status | Time Delay | Enter Current Quantity | Remarks | Planned | Actual |  | Time Delay | Remarks | Planned | Actual | PO Number | Time Delay | Remarks
2025-01-24 11:20 | IND-1001-001 | Jane Doe | P001 | Green Energy Plant | Steel Pipes (6-inch diameter) | 200 | 2025-01-30 | PipeSpecs.pdf | Ready-Made | 2025-01-24 15:20 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | Not In Stock | 0d 02:27 |  |  | 2025-01-25 17:48 | 2025-01-24 17:53 | Done | 0d 02:27 |  | 2025-01-25 11:53 | 2025-07-20 18:12 | 3022112 | 0 | Task Testing
2025-01-24 11:20 | IND-1002-001 | John Doe | P002 | Solar Power Plant | Solar Panel Mounting Frames | 50 | 2025-02-05 | FrameDetails.xlsx | Ready-Made | 2025-01-24 15:20 | 2025-02-11 11:09 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-02-11 11:13 | In Stock | 0d 02:27 |  |  | 2025-01-25 17:48 |  | Done | 0d 02:27 |  | 2025-01-25 11:53 |  |  | 0
2025-01-24 12:10 | IND-1003-001 | Alice Johnson | P003 | River Bridge Project | Concrete Mix (Grade M30) | 500 Bags | 2025-01-28 | MixSpecs.docx | Ready-Made | 2025-01-24 16:10 | 2025-01-24 17:53 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:53 | Done | 0d 02:27 |  |  | 2025-01-25 17:48 |  |  | 0d 02:27
2025-01-24 13:45 | IND-1004-002 | Bob Smith | P004 | Urban Road Project | Bitumen | 20 Tons | 2025-02-01 | BitumenData.pdf | Ready-Made | 2025-01-24 17:45 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | In Stock | 0d 02:27 |  |  | 2025-01-25 17:48 |  |  | 0d 02:27
2025-01-24 14:30 | IND-1005-001 | Jane Doe | P005 | Wind Turbine Project | High-Grade Bearings (Industrial) | 10 Sets | 2025-02-15 | BearingsSpec.docx | Tailor-Made | 2025-01-24 18:30 | 2025-01-20 17:57 | Accepted |  | Done | 2025-01-21 11:56 |  |  | -45679d 12:04
2025-01-24 15:05 | IND-1006-003 | John Doe | P006 | Office Tower Build | Reinforced Steel Bars (12mm diameter) | 300 Kg | 2025-01-31 | SteelDetails.pdf | Tailor-Made | 2025-01-25 09:05 | 2025-01-24 17:48 | Rejected | 0d 02:27 |  |  |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE! |  | #VALUE! |  |  | #VALUE!
2025-01-24 16:00 | IND-1007-001 | Alice Johnson | P007 | Coastal Refinery | High-Pressure Valves | 25 | 2025-02-10 | ValveSpecs.docx | Tailor-Made | 2025-01-25 10:00 | 2025-07-21 00:14 | Rejected | 176d 14:13 | Sample Test |  |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE! |  | #VALUE! |  |  | #VALUE!
2025-01-24 16:50 | IND-1008-002 | Bob Smith | P008 | Residential Complex | HVAC Systems (Centralized) | 12 | 2025-02-20 | HVACSpecs.xlsx | Tailor-Made | 2025-01-25 10:50 | 2025-01-24 17:48 | Rejected | 0d 02:27 |  |  | 2025-01-24 17:48 | In Stock but Order | #VALUE! |  |  | 2025-01-25 17:48 | 2025-01-24 17:48 | Done | 0d 02:27 |  | 2025-01-25 11:53 | 2025-01-24 17:49 | 101 | 0
2025-01-24 17:15 | IND-1009-001 | Jane Doe | P009 | Rural Electrification | Copper Cables (High Voltage) | 1000 Meters | 2025-02-08 | CableSpecs.pdf | Tailor-Made | 2025-01-25 11:15 | 2025-07-20 19:45 | Rejected | 176d 08:30 | Not Required |  |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE! |  | #VALUE! |  |  | #VALUE!
2025-01-24 18:30 | IND-1010-002 | John Doe | P010 | Factory Cooling System | Industrial Chillers | 8 Units | 2025-02-18 | ChillerSpecs.xlsx | Tailor-Made | 2025-01-25 12:30 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | In Stock but Order | 0d 02:27 |  |  | 2025-01-25 17:48 | 2025-01-24 17:53 | Done | 0d 02:27 |  | 2025-01-25 11:53 |  |  | 0
2025-01-24 19:05 | IND-1011-001 | Pattrick Snow | P011 | High-Speed Rail Project | High-Tensile Bolts and Nuts | 500 Sets | 2025-01-27 | BoltSpecs.docx | Tailor-Made | 2025-01-25 13:05 | 2025-01-24 17:48 | Rejected | 0d 02:27 |  |  | 2025-01-24 17:48 | Not In Stock | #VALUE! |  |  | 2025-01-25 17:48 | 2025-01-24 17:49 | Done | 0d 02:27 |  | 2025-01-25 11:53 | 2025-01-24 17:49 | 202 | 0
2025-01-24 19:50 | IND-1012-003 | Bruce Wayne | P012 | Airport Expansion | Aluminum Sheets (Aviation Grade) | 150 Sheets | 2025-02-14 | AluminumSpecs.pdf | Tailor-Made | 2025-01-25 13:50 | 2025-01-24 17:53 | Rejected | 0d 02:27 |  |  | 2025-01-24 17:53 | In Stock but Order | #VALUE! |  |  | 2025-01-25 17:52 |  |  | 0d 02:27 |  | #VALUE! |  |  | #VALUE!
2025-01-24 20:30 | IND-1013-001 | Jane Doe | P013 | Smart City Development | LED Street Lights | 300 Units | 2025-02-12 | LEDSpecs.xlsx | Tailor-Made | 2025-01-25 14:30 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | Not In Stock | 0d 02:27 |  |  | 2025-01-25 17:48 | 2025-01-24 17:48 | Done | 0d 02:27 |  | 2025-01-25 11:53 | 2025-01-24 17:53 | 404 | 0
2025-01-24 20:30 | IND-1013-001 | Jane Doe | P013 | Smart City Development | LED Street Lights | 300 Units | 2025-02-12 | LEDSpecs.xlsx | Tailor-Made | 2025-01-25 14:30 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | In Stock but Order | 0d 02:27 |  |  | 2025-01-25 17:48 |  |  | 0d 02:27
2025-01-24 21:10 | IND-1014-002 | Alice Johnson | P014 | Oil Rig Maintenance | Drilling Fluids | 50 Drums | 2025-02-09 | DrillingFluid.pdf | Tailor-Made | 2025-01-25 15:10 | 2025-01-24 17:53 | Rejected | 0d 02:27 |  |  |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE!
2025-01-24 22:45 | IND-1015-001 | Bob Smith | P015 | Port Authority Project | Dockside Cranes | 3 Units | 2025-03-01 | CraneSpecs.docx | Tailor-Made | 2025-01-25 16:45 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | Not In Stock | 0d 02:27 |  |  | 2025-01-25 17:48 |  |  | 0d 02:27
2025-01-24 23:30 | IND-1016-003 | John Doe | P016 | Dam Construction | Turbine Blades | 25 Blades | 2025-02-28 | TurbineSpecs.xlsx | Ready-Made | 2025-01-25 17:30 | 2025-01-24 17:53 | Rejected | 0d 02:27 |  |  | 2025-01-24 17:53 | Not In Stock | #VALUE! |  |  | 2025-01-25 10:52 | 2025-01-24 17:53 | Done | 0d 02:27 |  | 2025-01-25 11:53 |  |  | 0
2025-01-24 23:30 | IND-1016-003 | Alice Johnson | P016 | Dam Construction | Turbine Blades | 25 Blades | 2025-02-28 | TurbineSpecs.xlsx | Ready-Made | 2025-01-25 17:30 | 2025-01-24 17:48 | Accepted | 0d 02:27 |  | 2025-01-21 11:56 | 2025-01-24 17:48 | Not In Stock | 0d 02:27 |  |  | 2025-01-25 10:48 | 2025-01-24 17:49 | Done | 0d 02:27 |  | 2025-01-25 11:53 | 2025-01-24 17:49 | 303 | 0
Formulas:
Jane Doe ¦ John Doe = IF([What],IF(AND(HOUR([What]+K5)>9,(HOUR([What]+K5)<19)),[What]+K5,WORKDAY.INTL(INT([What]),1,"0000001",Holidays!A:A)+HOUR([What]+K5-B1)/24+MINUTE([What])/1440),"")
STEP 2 - Check Store Availablity = IF([Status]="Accepted",IF([Actual],IF(AND(HOUR([Actual]+P5)>9,(HOUR([Actual]+P5)<19)),[Actual]+P5,WORKDAY.INTL(INT([Actual]),1,"0000001",Holidays!A:A)+HOUR([Actual]+P5-B1)/24+MINUTE([Actual])/1440),""),"")
STEP 4 - PO Creation = IF([Actual],IF(AND(HOUR([Actual]+AA5)>9,(HOUR([Actual]+AA5)<19)),[Actual]+AA5,WORKDAY.INTL(INT([Actual]),1,"0000001",#REF!)+HOUR([Actual]+AA5-B1)/24+MINUTE([Actual])/1440),"")
STEP 4 - PO Creation = IF([Actual]="","",IF(AND(HOUR([Actual]+AA5)>9,HOUR([Actual]+AA5)<19),[Actual]+AA5,WORKDAY.INTL(INT([Actual]),1,"0000001",Holidays!A:A)+HOUR([Actual]+AA5-B1)/24+MINUTE([Actual]+AA5-B1)/1440))
Actual = IF([Status]="","",IF([Actual],[Actual],IF([Status]<>"",A1,"")))
Actual = IF(X7="","",IF([Actual],[Actual],IF(X7<>"",A1,"")))
STEP 3 - Float RFQ = IF([Item Type]="Tailor-Made",IF([Actual],WORKDAY.INTL([Actual],V5,"0000001",#REF!)+HOUR([Actual])/24+MINUTE([Actual])/1440,""),IF([Actual],IF(AND(HOUR([Actual]+W5)>9,(HOUR([Actual]+W5)<19)),[Actual]+W5,WORKDAY.INTL(INT([Actual]),1,"0000001",#REF!)+HOUR([Actual]+W5-B1)/24+MINUTE([Actual])/1440),""))

## Holidays
2024-10-02 | <---You can type the dates of the holidays here
2024-10-06
2024-10-13
2024-10-20
2024-10-27
2024-10-30
2024-10-31
2024-11-01
2024-11-02
2024-11-03
2024-11-10
2024-11-16
2024-11-17
2024-11-24
2024-12-01
2024-12-07
2024-12-08
2024-12-15
2024-12-21
2024-12-22
2024-12-25
2024-12-29
2025-01-04
2025-01-18
2025-02-01
2025-02-15
2025-03-01
2025-03-15
2025-04-05
2025-04-19
2025-05-03
2025-05-17
2025-06-07
2025-06-21
2025-07-05
2025-07-19
2025-08-02
2025-08-16
2025-09-06
2025-09-20
2025-10-04
2025-10-18
2025-11-01
2025-11-15
2025-12-06
2025-12-20